## Dashboard
Modules List | Feature Count | Total Cases | Pass | Fail | Not in scope
Amigo App & Ebike | OTP | 30 | 30 | 0 | 0 | Total Test Case | 236
| Userbike | 26 | 26 | 0 | 0 | Total Executed | 200
| Rides | 23 | 23 | 0 | 0 | Total Pending | 36
| Fiteness | 18 | 17 | 0 | 0 | Execution Progress % | 84.7458
| Config | 7 | 7 | 0 | 0
| Notifications | 28 | 28 | 0 | 0
| Ride modes | 11 | 11 | 0 | 0
| Child mode | 11 | 11 | 0 | 0
| Map components | 36 | 36 | 0 | 0
| Community | 16 | 7 | 0 | 0
| Database Testing | 30 | 4 | 26
Total | 11 | 236 | 200 | 26 | 0

## Testcase Execution count
Date | Test Case Execution Count | Pass | Fail | Total Count
15-02-2024 | 44 | 15 | 29 | 44
19-02-2024 | 47 | 47 | 0 | 91
20-02-2024
21-02-2024
22-02-2024
23-02-2024
24-02-2024
25-02-2024
26-02-2024

## OTP
| Priority | Category/ module | Test Type | API Name | Test Objectives | Test procedure | API End Point | Auth | Request Body | Expected Status Code | Expected Response Body | Expected Result | Actual Result | Status | Bug id | Tested By | Tested on
EMB_01 | P0 | HOme.Login.Etc | API | OTP | Verify that the response status code is 200. | 1. Hit the API | /v1/send-otp | NA | { "phone": "+917092878753" } | 200 | { "token": "v4.public.e" } | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMB_02 | P1 |  | API | OTP | Verify that the "status" field in the response is "success." | 1. Hit the API | /v1/send-otp | NA | { "phone": "+917092878753" } | 200 | { "token": "v4.public.e" } | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMB_03 | P1 |  | API | OTP | Verify that message field contains "OTP Sucessfully" | 1. Hit the API | /v1/send-otp | NA | { "phone": "+917092878753" } | 200 | { "token": "v4.public.e" } | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMB_04 | P1 |  | API | OTP | Verify that a valid OTP is present in the response | 1. Hit the API | /v1/send-otp | NA | { "phone": "+917092878753" } | 200 | { "token": "v4.public.e" } | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMB_05 | P0 |  | API | OTP | Verify that the response status code is 400 (Bad Request) | 1. Hit the API | /v1/send-otp | NA | Invalid format | 400 | "message": "field: Phone, expected required" | "field: Phone, expected e164" | Status Code:400 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMB_06 | P1 |  | API | OTP | Verify that the "status" field in the response is "error." | 1. Hit the API | /v1/send-otp | NA | Invalid format | 400 | "message": "field: Phone, expected required" | "error": true, "message": "field: Phone, expected e164"} | Status Code:400 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMB_07 | P1 |  | API | OTP | Ensure that the "message" field contains "Mobile number is required." | 1. Hit the API | /v1/send-otp | NA | Invalid format | 400 | "message": "field: Phone, expected required" | "error": true, "message": "field: Phone, expected required" | Status Code:400 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMB_08 | P1 |  | API | OTP | Verify that the response status code is 400 (Bad Request) ,while updating the invalid mobile number . | 1. Hit the API | /v1/send-otp | NA | Invalid format | 400 | "message": "field: Phone, expected required" | "error": true, "message": "field: Phone, expected required"} | Status Code:400 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMB_09 | P0 |  | API | OTP | Verify that the "status" field in the response is "error", while update the invalid mobile number. | 1. Hit the API | /v1/send-otp | NA | Invalid format | 400 | "message": "field: Phone, expected required" | "error": true, "message": "field: Phone, expected required"} | Status Code:400 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMB_10 | P0 |  | API | OTP | Verify that that the "message" field contains "Invalid mobile number format." | 1. Hit the API | /v1/send-otp | NA |  | 400 | "message": "field: Phone, expected required" |  | Status Code: Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMB_11 | P0 |  | API | OTP | Verify that the response status code is 429 when the user tried (Too Many Requests). | 1. Hit the API | /v1/send-otp | NA |  | 429 |  |  | Status Code: Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMB_12 | P1 |  | API | OTP | Verify that the status" field in the response is error", while user tried too many login request | 1. Hit the API | /v1/send-otp | NA |  | 429 |  |  | Status Code: Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMB_14 | P1 |  | API | OTP | Verify that the message field contains " Token has expired. Please reauthenticate." while token was expired | 1. Hit the API |  |  |  | 400 |  |  | Status Code: Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMB_15 | P1 |  | API | OTP | Verify that the message "Invalid Otp" while updating the invalid otp | 1. Hit the API | v1/verify-otp | NA |  | 419 | No -Auth | message": "invalid otp" | Status Code:419 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMB_16 | P1 |  | API | OTP | Verify that the message "expired token" while user without updating the OTP | 1. Hit the API | v1/verify-otp | NA |  | 401 |  | Need to check with backend team for exact result | Status Code:401 Response Body: | Pass | "message": "invalid character '}' looking for beginning of value" | Karthikeyan k | 2024-05-02
EMB_17 | P1 |  | API | OTP | Verify that message "expired token " while user update charcters instead of OTP | 1. Hit the API | v1/verify-otp | NA |  | 401 |  | "message": "expired token" | Status Code:401 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMB_18 | P1 |  | API | OTP | Verify the message "expired token" while user update the OTP after 2 minutes | 1. Hit the API | v1/verify-otp | NA |  | 401 |  | "message": "expired token" | Status Code:401 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMB_19 | P1 |  | API | OTP | Verify that the message ""field: Phone, expected required" while user not updating the mobile number | 1. Hit the API | v1/verify-otp | NA |  | 400 |  | Need to check with backend team for exact result | Status Code:401 Response Body: | Pass | "message": "invalid character '}' looking for beginning of value" | Karthikeyan k | 2024-05-02
EMB_20 | P1 |  | API | OTP | Verify that status code is 400 ,while user wasn't updating the mobile number | 1. Hit the API | v1/verify-otp | NA |  | 400 |  | "message": "invalid character '}' looking for beginning of value" | Status Code:400 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMB_21 | P0 |  | API | OTP | Verify that message "field: Phone, expected e164", while user updating the invalid phone number | 1. Hit the API | v1/verify-otp | NA |  | 400 |  | "message": "field: Phone, expected e164" | Status Code:400 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMB_22 | P1 |  | API | OTP | Verify that the status code will be 400 , while user update the invalid phone number | 1. Hit the API | v1/verify-otp | NA |  | 400 |  | "message": "field: Phone, expected e164" | Status Code:400 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMB_23 | P1 |  | API | OTP | Verify that the message "field: Phone, expected e164" , while user update the phone number without country code | 1. Hit the API | v1/verify-otp | NA |  | 400 |  | "message": "field: Phone, expected e164" | Status Code:400 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMB_24 | P1 |  | API | OTP | Verify that the status code will be 400 ,while user update the phone number without country code . | 1. Hit the API | v1/verify-otp | NA |  | 400 |  | "message": "field: Phone, expected e164" | Status Code:400 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMB_25 | P1 |  | API | OTP | Verify that the access token , and refresh token while the user updating the OTP. | 1. Hit the API | v1/verify-otp | NA |  | 200 |  | "access_token" & "refresh_token": "v4.public. | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMB_26 | P1 |  | API | OTP | Verify that the new user Will be "False" ,while user updating the OTP (False indicates Existing user) | 1. Hit the API | v1/verify-otp | NA |  | 200 |  | "new_user": false, "bike_vin": "E13456677" | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMB_27 | P1 |  | API | OTP | Verify that the Bike VIN will update on the response body ,while the user updating the otp . | 1. Hit the API | v1/verify-otp | NA |  | 200 |  | "new_user": false, "bike_vin": "E13456677" | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMB_28 | P0 |  | Database | OTP | Verify that the system allows users to log in with a valid mobile phone number. | [8 empty] | Pass |  | Karthikeyan k | 2024-05-02
EMB_29 | P0 |  | Database | OTP | Verify that the system does not allow users to log in with an invalid mobile number | [8 empty] | Pass |  | Karthikeyan k | 2024-05-02
EMB_30 | P0 |  | Database | OTP | Verify that the system does not allow users to log in with an empty mobile number field. | [8 empty] | Pass |  | Karthikeyan k | 2024-05-02
EMB_31 | P0 |  | Database | OTP | Verify that the system sends a verification code to the user's mobile phone and requires input for successful login. | [8 empty] | Pass |  | Karthikeyan k | 2024-05-02
EMB_32 | P0 |  | API

## Userbike
Test Case ID | Priority | Category/ module | Test Type | API Name | Test Objectives | Test procedure | API End Point | Auth | Request Body | Expected Status Code | Expected Response Body | Expected Result | Actual Result | Status | Bug id | Tested By | Tested on
EMBU_01 | P0 | Userbike | API | User bike | Verify the status code is code is 200 when the user updates the correct mobile number and otp | 1. Hit the API | verify-otp | NA |  | 200 | "access_token": "v4.public. | "access_token": "v4.public. | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMBU_02 | P0 | Userbike | API | User bike | Verify that the user is existing or new user on the response body | 1. Hit the API | verify-otp | NA |  | 200 | "access_token": "v4.public. | "new_user": false, "bike_vin": "E13456677"} | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMBU_03 | P1 | Userbike | API | User bike | verify that the user can view the Bike Vin if the user is existing user | 1. Hit the API | verify-otp | NA |  | 200 | "access_token": "v4.public. | "new_user": false, "bike_vin": "E13456677"} | Status Code: Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMBU_04 | P1 | Userbike | API | User bike | Verify Valid User Login and Retrieve Profile | 1. Hit the API | userbike/v1/ | Inherit form parent |  | 200 | To view the Bike information | "vin": "E13456677", "model": "x1", "color": "blue", "nickname": "karthik47", "last_connection": 0, | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMBU_05 | P1 | Userbike | API | User bike | Verify that the status will be "success" ,While Perform a valid user login to obtain an authentication token. | 1. Hit the API | userbike/v1/ | Inherit form parent |  | 200 | To view the Bike information | "vin": "E13456677", "model": "x1", "color": "blue", "nickname": "karthik47", "last_connection": 0, | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMBU_06 | P1 | Userbike | API | User bike | Verify that the obtained authentication token to retrieve the user profile details. | 1. Hit the API | userbike/v1/ | Inherit form parent |  | 200 | Inherit auth from parent | "vin": "E13456677", "model": "x1", "color": "blue", "nickname": "karthik47", "last_connection": 0, | Status Code: Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMBU_07 | P0 | Userbike | API | User bike | Unauthorized Access without Token | 1. Hit the API | userbike/v1/ | Inherit form parent |  | 401 | NO Auth | "error": true, "message": "invalid token" | Status Code:401 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMBU_08 | P1 | Userbike | API | User bike | Verify that the status will be "error " while Attempt to retrieve user profile without providing an authentication token. | 1. Hit the API | userbike/v1/ | Inherit form parent |  | 401 | NO Auth | "error": true, "message": "invalid token" | Status Code:401 Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMBU_09 | P1 | Userbike | API | User bike | Verify that the message field contains ""Unauthorized. Please provide a valid authentication token." | 1. Hit the API | userbike/v1/ | Inherit form parent |  | 401 | NO Auth | "error": true, "message": "invalid token" | Status Code: Response Body: | Pass |  | Karthikeyan k | 2024-02-02
EMBU_11 | P1 | Userbike | API | User bike | Verify that the status will be "error " while Invalid User Login and Profile Retrieval | 1. Hit the API | userbike/v1/ |  |  | 400 |  |  | Status Code: Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMBU_12 | P1 | Userbike | API | User bike | Verify the expired Token | 1. Hit the API | verify-otp | NA |  | 401 | NO -Auth | "error": true, "message": "expired token" | Status Code:401 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMBU_13 | P1 | Userbike | API | User bike | verify the status will be "Error" while token was expired. | 1. Hit the API | verify-otp | NA |  | 401 | NO -Auth | error": true, "message": "expired token" | Status Code:401 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMBU_14 | P1 | Userbike | API | User bike | Verify that the API returns the correct user profile when a valid phone number is updated. | 1. Hit the API | userbike/v1/ |  |  | 200 |  | "access_token" & "refresh_token": "v4.public. | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMBU_15 | P1 | Userbike | API | User bike | Verify that the response status code is 200(OK) ,when a valid phone number is updated | 1. Hit the API | userbike/v1/ |  |  | 200 | No-Auth | token":"v4.public. | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMBU_16 | P0 | Userbike | API | User bike | Validate the response JSON structure and ensure it contains the expected fields such as username, email, and other relevant profile information. | 1. Hit the API | userbike/v1/ |  |  | 200 | inherit from parent | View the username , phone ,gender and email | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMBU_17 | P1 | Userbike | API | User bike | Verify that the returned user profile details match the expected values. | 1. Hit the API | userbike/v1/ |  |  | 200 | inherit from parent | Profile details | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 2024-05-02
EMR_01 | P0 | Userbike | API | Userbike | Verify the status code is 200 on rides | 1. Hit the API | /ride/v1/trips?start=&end= |  |  |  |  | 200 | Working as expected | Pass |  | Karthikeyan k | 15/02/2024
| P0 | Userbike | API | Userbike | Verify the user profile details is updated ,if the status code is 200 | 1. Hit the API | /ride/v1/trips?start=&end= |  |  |  |  | 200 | Working as expected | Pass |  | Karthikeyan k | 15/02/2024
| P0 | Userbike | API | Userbike | Verify the user profile data is correctly updated , if the APi get success | 1. Hit the API | /ride/v1/trips?start=&end= |  |  |  |  | 200 | Working as expected | Pass |  | Karthikeyan k | 15/02/2024
| P0 | Userbike | API | Userbike | Verify the status code is 400 , If the API get errors | 1. Hit the API | /ride/v1/trips?start=&end= |  |  |  |  | 400 | Working as expected | Pass |  | Karthikeyan k | 15/02/2024
| P0 | Userbike | API | Userbike | Verify the message fields update the "gocql: no hosts available in the pool" ,If The ApI get errors | 1. Hit the API | /ride/v1/trips?start=&end= |  |  |  |  | 400 | Working as expected | Pass |  | Karthikeyan k | 15/02/2024
| P1 | Userbike | API | Userbike | Verify the user profilre didn't updated ,if API get error (Bad request) | 1. Hit the API | /ride/v1/trips?start=&end= |  |  |  |  | 400 | Working as expected | Pass |  | Karthikeyan k | 15/02/2024
| P1 | Userbike | API | User bike | Verify the user Vin , If the response code is 200 | 1. Hit the API | /ride/v1/trips?start=&end= |  |  |  |  | 200 | Working as expected | Pass |  | Karthikeyan k | 15/02/2024
| P1 | Userbike | API | User bike | Veirfy the user Bike model and color , If the response code is200 | 1. Hit the API | /ride/v1/trips?start=&end= |  |  |  |  | 200 | Working as expected | Pass |  | Karthikeyan k | 15/02/2024
| P1 | Userbike | API | User bike | Verify the user nick name is updated correctly , If the response code is 200 | 1. Hit the API | /ride/v1/trips?start=&end= |  |  |  |  | 200 | Working as expected | Pass |  | Karthikeyan k | 15/02/2024
| P1 | Userbike | API | User bike | Verify the bike image colour updated correctly ,if the response code is 200 | 1. Hit the API | /ride/v1/trips?start=&end= |  |  |  |  | 200 | Working as expected | Pass |  | Karthikeyan k | 15/02/2024

## Rides
Test Case ID | Priority | Category/ module | Test Type | API Name | Test Objectives | Test procedure | API End Point | Auth | Request Body | Expected Status Code | Expected Response Body | Expected Result | Actual Result | Status | Bug id | Tested By | Tested on
EMR_01 | P0 | Rides | API | Rides | Check the status code is 200 , If user the existing ride details | 1. Hit the API | /ride/v1/trips?start=&end= | Bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_02 | P1 | Rides | API | Rides | Verify that the trip ID is updated sucessfully , If the status code is 200 | 1. Hit the API | /ride/v1/trips?start=&end= | Bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_03 | P1 | Rides | API | Rides | Verify that the info [Title of the ride ] ,If the status code is 200 | 1. Hit the API | /ride/v1/trips?start=&end= | Bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_04 | P1 | Rides | API | Rides | Verify that the start time of the ride , if the status code is 200 | 1. Hit the API | /ride/v1/trips?start=&end= | Bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_05 | P1 | Rides | API | Rides | Verify the end time of the ride , If the status code is 200 | 1. Hit the API | /ride/v1/trips?start=&end= | Bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_06 | P1 | Rides | API | Rides | Verify the bike vin ,If the status code is 200 | 1. Hit the API | /ride/v1/trips?start=&end= | Bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_07 | P1 | Rides | API | Rides | Verify the distance of the ride ,if the status code is 200 | 1. Hit the API | /ride/v1/trips?start=&end= | Bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_08 | P1 | Rides | API | Rides | Verify the start location of the ride , If the status code is 200 | 1. Hit the API | /ride/v1/trips?start=&end= | Bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_09 | P1 | Rides | API | Rides | Verify the end location of the ride , if the status code | 1. Hit the API | /ride/v1/trips?start=&end= | Bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_10 | P1 | Rides | API | Rides | Verify the image ,if the status code is 200 | 1. Hit the API | /ride/v1/trips?start=&end= | Bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_11 | P1 | Rides | API | Rides | Verify the status code is 401 , if API expries the token | 1. Hit the API | /ride/v1/trips?start=&end= | Bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_12 | P1 | Rides | API | Rides | Verify the message "expired token" ,IF status code is 401 | 1. Hit the API | /ride/v1/trips?start=&end= | Inherit from auth | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_13 | P0 | Rides | API | Rides | Verify the latest trip id ,If the status code is 200 | 1. Hit the API | /ride/v1/trips/latest | Inherit from auth | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_14 | P1 | Rides | API | Rides | Verify the info of the latest trip , If the status code is 200 | 1. Hit the API | /ride/v1/trips/latest | Inherit from auth | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_15 | P1 | Rides | API | Rides | Verify the start time of the latest trip , If the status code is 200 | 1. Hit the API | /ride/v1/trips/latest | Inherit from auth | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_16 | P1 | Rides | API | Rides | Verify the end time of the latest trip ,If the status code is 200 | 1. Hit the API | /ride/v1/trips/latest | Inherit from auth | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_17 | P1 | Rides | API | Rides | Verify the Bike Vin of the latest trip , If the status code is 200. | 1. Hit the API | /ride/v1/trips/latest | Inherit from auth | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_18 | P1 | Rides | API | Rides | Verify the start location of the latest trip ,If the status code is 200 | 1. Hit the API | /ride/v1/trips/latest | Inherit from auth | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_19 | P1 | Rides | API | Rides | Verify that the end location of the latest trip ,if the status code is 200 | 1. Hit the API | /ride/v1/trips/latest | Inherit from auth | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_20 | P1 | Rides | API | Rides | Verify that the Route map image , If the status code is 200 | 1. Hit the API | /ride/v1/trips/latest | Inherit from auth | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_21 | P1 | Rides | API | Rides | Verify that the latest ride image ,If the status code is 200 | 1. Hit the API | /ride/v1/trips/latest | Inherit from auth | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_22 | P1 | Rides | API | Rides | Verify that the status code is 403 , If API get error | 1. Hit the API | /ride/v1/trips/latest | Inherit from auth | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024
EMR_23 | P1 | Rides | API | Rides | Verify that the message is unauthorised , If API get error | 1. Hit the API | /ride/v1/trips/latest | Inherit from auth | { "phone": "+917092878753" } | 403 |  | API should be functionally working with correct status code and respose body | Working as expected | Pass |  | Karthikeyan k | 19/02/2024

## Fiteness
Test Case ID | Priority | Category/ module | Test Type | API Name | Test Objectives | Test procedure | API End Point | Auth | Request Body | Expected Status Code | Expected Response Body | Expected Result | Actual Result | Status | Bug id | Tested By | Tested on
EMF_01 | P0 | Fitness | API | Fiteness | Verify that the status code is 200 , If the user hits the fiteness API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_02 | P1 | Fitness | API | Fiteness | Verify that the distance , if the user hits the fiteness API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_03 | P1 | Fitness | API | Fiteness | Verify that the universe distance ,If the user hits the fitness API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_04 | P1 | Fitness | API | Fiteness | Verify that the speed , if the user hits the API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_05 | P1 | Fitness | API | Fiteness | Verify that the universal speed , if the user hits the API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_06 | P1 | Fitness | API | Fiteness | Verify that the savings If the user hits the API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_07 | P1 | Fitness | API | Fiteness | Verify that the universal savings ,If the user hits the API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_08 | P1 | Fitness | API | Fiteness | Verify the co2 saved ,If the user hits the API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/ 02/2024
EMF_09 | P1 | Fitness | API | Fiteness | Verify the universal co2 saved , If the user hits the API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_10 | P1 | Fitness | API | Fiteness | Verify the effort , If the user hits the API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_11 | P1 | Fitness | API | Fiteness | Verify the universal effort , If the user hits the API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_12 | P1 | Fitness | API | Fiteness | Verify that the calories ,If the user hits the API [Fiteness ] | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_13 | P1 | Fitness | API | Fiteness | Verify that the universal calories , If the user hits the API [Fiteness ] | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_14 | P1 | Fitness | API | Fiteness | Verify that the graph data min value , If the user hits the API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_15 | P1 | Fitness | API | Fiteness | Verify that the graph data max value , If the user hits the API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
EMF_16 | P1 | Fitness | API | Fiteness | Verify that the date ,If the user hits the API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
|  |  | API | Fiteness | Verify that the month , If the user hits the API | Hit the API | }/fitness/v1/goal/ | bearer token | "{ ""phone"": ""+917092878753"" }" | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 21/02/2024
|  |  | API | Fiteness

## Map components
| Priority | Category/ module | Test Type | API Name | Test Objectives | Test procedure | API End Point | Auth | Request Body | Expected Status Code | Expected Response Body | Expected Result | Actual Result | Status | Bug id | Tested By | Tested on
EMM_01 | P0 |  | API | Map components | Verify that status code is 200 while API hit suceesfully | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Status code :200 | Pass |  | Karthikeyan k | 19/02/2024
EMM_02 | P1 |  | API | Map components | Verify that the home location details present if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | Status code :200 | Pass |  | Karthikeyan k | 19/02/2024
EMM_03 | P1 |  | API | Map components | Verify that the id of the home location , if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | status code :200 | Pass |  | Karthikeyan k | 19/02/2024
EMM_04 | P1 |  | API | Map components | Verify that the home location details , if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | status code :200 | Pass |  | Karthikeyan k | 19/02/2024
EMM_05 | P1 |  | API | Map components | Verify that the longitude of the home location, if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | status code :200 | Pass |  | Karthikeyan k | 19/02/2024
EMM_06 | P1 |  | API | Map components | Verify that the latitude of the home location , if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | status code :200 | Pass |  | Karthikeyan k | 19/02/2024
EMM_07 | P1 |  | API | Map components | Verify that the favorite status of the location , if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | status code :200 | Pass |  | Karthikeyan k | 19/02/2024
EMM_08 | P1 |  | API | Map components | Verify that the work location details present if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | status code :200 | Pass |  | Karthikeyan k | 19/02/2024
EMM_09 | P1 |  | API | Map components | Verify that the work location details , if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | status code :200 | Pass |  | Karthikeyan k | 19/02/2024
EMM_10 | P1 |  | API | Map components | Verify that the longitude of the work location, if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body | status code :200 | Pass |  | Karthikeyan k | 19/02/2024
EMM_11 | P1 |  | API | Map components | Verify that the latitude of the work location , if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_12 | P1 |  | API | Map components | Verify that the favorite status of the location , if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_13 | P1 |  | API | Map components | Verify that the id of the favorite location ,if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_14 | P1 |  | API | Map components | Verify that the favorite location details , if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_15 | P1 |  | API | Map components | Verify that the latitude of the favorite location , if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_16 | P1 |  | API | Map components | Verify that the longitude of the favorite location ,If the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_17 | P1 |  | API | Map components | Verify that the favorite status of the location , If the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_18 | P1 |  | API | Map components | Verify that the saved location id , if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_19 | P1 |  | API | Map components | Verify that the saved location details , If the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_20 | P1 |  | API | Map components | Verify that the latitude of the saved location , If the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_21 | P1 |  | API | Map components | Verify the longitude of the saved location, if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_22 | P1 |  | API | Map components | Verify that the favorite status,if the status code is 200 | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_23 | P1 |  | API | Map components | Verify that the status code is 401,If the API get fails | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_24 | P1 |  | API | Map components | Verify that the status message ,IF API gets fails | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 19/02/2024
EMM_25 | P0 |  | API | Map components | Verify that the all favorites location'a will fetch correctly , If the user hits the API [Map components] | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 22/02/2024
EMM_26 | P0 |  | API | Map components | Verify that the all saved locations will fetch correctly ,If the user hits the API[Map component] | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 22/02/2024
EMM_27 | P1 |  | API | Map components | Verify that the favorite location ID will be different ,If the user hits the API[Map component] | 1. Hit the API | /mapcomponents/v1/location | bearer token | { "phone": "+917092878753" } | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 22/02/2024
EMM_28 | P1 |  | API | Map components | Verify that the favorite location will be updated correctly for all the favorite locations , If the user hits the API | 1. Hit the API | /mapcomponents/v1/location | bearer token |  | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 22/02/2024
EMM_29 | P1 |  | API | Map components | Verify that the favorite location latitude will be updated for all the favorite locations ,If user hits the API | 1. Hit the API | /mapcomponents/v1/location | bearer token |  | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 22/02/2024
EMM_30 | P1 |  | API | Map components | Verify that the favorite location longitude will be updated for all the favorite locations ,If user hits the API | 1. Hit the API | /mapcomponents/v1/location | bearer token |  | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 22/02/2024
| P1 |  | API | Map components | Verify that the favorite status will be updated for all the favorite locations,If the user hits the API | 1. Hit the API | /mapcomponents/v1/location | bearer token |  | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 22/02/2024
| P1 |  | API | Map components | Verify that the saved location ID will be different ,If the user hits the API | 1. Hit the API | /mapcomponents/v1/location | bearer token |  | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 22/02/2024
| P1 |  | API | Map components | Verify that the saved location will be updated for all the saved locations ,If the user HIts the API | 1. Hit the API | /mapcomponents/v1/location | bearer token |  | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 22/02/2024
| P1 |  | API | Map components | Verify that the saved location latitude will be updated for all the saved locations , If the user hits the API | 1. Hit the API | /mapcomponents/v1/location | bearer token |  | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 22/02/2024
| P1 |  | API | Map components | Verify that the saved location longtitude will be updated for all the saved locations ,If the user hits the API | 1. Hit the API | /mapcomponents/v1/location | bearer token |  | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 22/02/2024
| P1 |  | API | Map components | Verify that the favorite status will be updated for all the locations ,If the user hits the API | 1. Hit the API | /mapcomponents/v1/location | bearer token |  | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 22/02/2024

## Database testing
Test Case ID | Priority | Category/ module | Test Type | API Name | Test Objectives | Test procedure | Expected Result | Actual Result | Status | Bug id | Tested By | Tested on
EMB_50 | P0 | Database /cloud | Database | OTP | Verify that the system allows users to log in with a valid mobile phone number. |  |  |  | Pass |  | Karthikeyan k | 2024-05-02
EMB_51 | P0 | Database /cloud | Database | OTP | Verify that the system does not allow users to log in with an invalid mobile number |  |  |  | Pass |  | Karthikeyan k | 2024-05-02
EMB_52 | P0 | Database /cloud | Database | OTP | Verify that the system does not allow users to log in with an empty mobile number field. |  |  |  | Pass |  | Karthikeyan k | 2024-05-02
EMB_53 | P0 | Database /cloud | Database | OTP | Verify that the system sends a verification code to the user's mobile phone and requires input for successful login. |  |  |  | Pass |  | Karthikeyan k | 2024-05-02
EMB_55 | P0 | Database /cloud | Database | User bike | Verify that user data in the database remains consistent after a successful mobile number login. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-397 | Karthikeyan k | 15/02/2024
EMB_56 | P1 | Database /cloud | Database | User bike | Verify that the user Bike VIN will be Updating correctly on the database . |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-398 | Karthikeyan k
EMB_57 | P1 | Database /cloud | Database | User bike | Verify that the user EM-Bike model will be Updating Correctly on the database. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-399 | Karthikeyan k
EMB_58 | P1 | Database /cloud | Database | User bike | Verify that the user EM-Bike colour Will be Updating correctly on the data base. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-400 | Karthikeyan k
EMB_59 | P1 | Database /cloud | Database | User bike | Verify that the user Bike Nick name will be Updating correctly on the data base. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-401 | Karthikeyan k
EMB_60 | P1 | Database /cloud | Database | User bike | Verify that the user BIke MQQt Password will be Updating correctly on the database. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-402 | Karthikeyan k
EMB_61 | P1 | Database /cloud | Database | User bike | Verify that the user EM-BIke's Last connection details will be updating on the data base. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-403 | Karthikeyan k
EMB_62 | P1 | Database /cloud | Database | User bike | Verify that the user EM-Bike Created Date details will be updating on the Data base. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-404 | Karthikeyan k
EMB_63 | P1 | Database /cloud | Database | User bike | Verify that the user Em-bike Modified date details will be updating on the data base. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-405 | Karthikeyan k
EMB_64 | P0 | Database /cloud | Database | User bike | Verify that the new user profile details were updated on the database. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-406 | Karthikeyan k
EMB_65 | P1 | Database /cloud | Database | User bike | Verify that the doodlev2 model EM --bike will be updating Black colour |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-407 | Karthikeyan k
EMB_66 | P1 | Database /cloud | Database | User bike | Verify that the emx model EM-Bike will be updating aqua (or0 neon colour |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-408 | Karthikeyan k
EMB_67 | P1 | Database /cloud | Database | User bike | Verify that the Trexplus EM-bike will be updating red colour |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-409 | Karthikeyan k
EMB_68 | P1 | Database /cloud | Database | User bike | Verify that the x1 EM-Bike will be updating Blue (or) Yellow colour |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-410 | Karthikeyan k
EMB_69 | P1 | Database /cloud | Database | User bike | Verify that the X2 EM-Bike will be updating red colour |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-411 | Karthikeyan k
EMB_70 | P1 | Database /cloud | Database | User bike | Verify that the X3 EM-Bike will be updating gold (or) silver colour |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-412 | Karthikeyan k
EMB_71 | P0 | Database /cloud | Database | User bike | Verify the user mobile number will be updating on the database. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-413 | Karthikeyan k
EMB_72 | P0 | Database /cloud | Database | User bike | Verify the user gender will be correctly updating on the database. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-414 | Karthikeyan k
EMB_73 | P1 | Database /cloud | Database | User bike | Verify the user height will be correctly updating on the database. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-415 | Karthikeyan k
EMB_74 | P1 | Database /cloud | Database | User bike | Verify the user weight will be correctly updating on the database. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-416 | Karthikeyan k
EMB_75 | P1 | Database /cloud | Database | OTP | Verify the user DOB will be correctly updating on the database. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-417 | Karthikeyan k
EMB_76 |  |  | Database |  | Verify the user health will be correctly updating on the database. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-418 | Karthikeyan k
EMB_77 |  |  | Database |  | Verify the user favorite fitness correctly updating on the database. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-419 | Karthikeyan k
EMB_78 |  |  | Database |  | Verify the user picture correctly updating on the database. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-420 | Karthikeyan k
EMB_79 |  |  | Database |  | Verify that the user Level will be correctly updating on the database. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-421 | Karthikeyan k
EMB_80 |  |  | Database |  | Verify that the user Email will be correctly updating on the database. |  |  | New User Details Not Fetching in PostgreSQL | Fail | https://em-techblr.atlassian.net/browse/EM-422 | Karthikeyan k

## Garage
Test Case ID | Priority | Category/ module | Test Type | API Name | Test Objectives | Test procedure | API End Point | Auth | Request Body | Expected Status Code | Expected Response Body | Expected Result | Actual Result | Status | Bug id | Tested By | Tested on
EMG_01 | P0 | Garage | API | Garage (Smart lock) | Verify that the status code is 200 , If the user hits the API | Verify that the response status code is 200. | /garage/v1/logs/lock | Bearer token | { "phone": "+917092878753" } | 200 | API should be functionally working with correct status code and respose body |  | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 20/02/2024
EMG_02 | P1 | Garage | API | Garage (Smart lock) | Verify that the Proximity settings , if the user hits the API |  | /garage/v1/logs/lock | Bearer token | { "phone": "+917092878753" } | 200 | API should be functionally working with correct status code and respose body |  |  | Pass |  | Karthikeyan k | 20/02/2024
EMG_03 | P1 | Garage | API | Garage (Smart lock) | Verify that the proximity settings status (true or false ) ,If the user hits the API |  | /garage/v1/logs/lock | Bearer token | { "phone": "+917092878753" } | 200 | API should be functionally working with correct status code and respose body |  |  | Pass |  | Karthikeyan k | 20/02/2024
EMG_04 | P1 | Garage | API | Garage (Smart lock) | Verify that the manual status , If the user hits the API |  | /garage/v1/logs/lock | Bearer token | { "phone": "+917092878753" } | 200 | API should be functionally working with correct status code and respose body |  |  | Pass |  | Karthikeyan k | 20/02/2024
EMG_05 | P1 | Garage | API | Garage (Smart lock) | Verify that the logged time & date , If the user hit the API |  | /garage/v1/logs/lock | Bearer token | { "phone": "+917092878753" } | 200 | API should be functionally working with correct status code and respose body |  |  | Pass |  | Karthikeyan k | 20/02/2024
EMG_06 | P1 | Garage | API | Garage (Smart lock) | Verify that the logged status[Locke status] , If the user hit the API |  | /garage/v1/logs/lock | Bearer token | { "phone": "+917092878753" } | 200 | API should be functionally working with correct status code and respose body |  |  | Pass |  | Karthikeyan k | 20/02/2024
|  |  | API | Garage (Smart lock) | Verify that the logged status [Unlocked],If the user hit the API |  | /garage/v1/logs/lock | Bearer token | { "phone": "+917092878753" } | 200 | API should be functionally working with correct status code and respose body |  |  | Pass |  | Karthikeyan k | 20/02/2024
|  |  | API | Garage[Range] | Verify that the model of the E-bike , If the user hit the API |  | /garage/v1/logs/lock | Bearer token | { "phone": "+917092878753" } | 200 | API should be functionally working with correct status code and respose body |  |  | Pass |  | Karthikeyan k | 20/02/2024
|  |  | API | Garage(Service) | Verify that the date, If the user hits the API[Battery life cycle] |  | /garage/v1/logs/lock | Bearer token | { "phone": "+917092878753" } | 200 | API should be functionally working with correct status code and respose body |  |  | Pass |  | Karthikeyan k | 20/02/2024
|  |  | API | Garage(Service) | Verify that the first max soc , If user hit the API[Battery life cycle] |  | /garage/v1/logs/lock | Bearer token | { "phone": "+917092878753" } | 200 | API should be functionally working with correct status code and respose body |  |  | Pass |  | Karthikeyan k | 20/02/2024
|  |  | API | Garage(Service) | Verify that the first min soc , If the user hit the API [Battery life cycle ] |  | /garage/v1/logs/lock | Bearer token | { "phone": "+917092878753" } | 200 | API should be functionally working with correct status code and respose body |  |  | Pass |  | Karthikeyan k | 20/02/2024
|  |  | API | Garage(Service) | Verify that the last max soc ,If the user hit the API [Battery life cycle] |  | /garage/v1/logs/lock | Bearer token | { "phone": "+917092878753" } | 200 | API should be functionally working with correct status code and respose body |  |  | Pass |  | Karthikeyan k | 20/02/2024
|  |  | API | Garage(Service) | Verify that the last min soc , If the user hit the API[Battery life cycle] |  | /garage/v1/logs/lock | Bearer token | { "phone": "+917092878753" } | 200 | API should be functionally working with correct status code and respose body |  |  | Pass |  | Karthikeyan k | 20/02/2024
API
API
API

## Config
Test Case ID | Priority | Category/ module | Test Type | API Name | Test Objectives | Test procedure | API End Point | Auth | Request Body | Expected Status Code | Expected Response Body | Expected Result | Actual Result | Status | Bug id | Tested By | Tested on
EMC_01 | P0 |  | API | Config | Verify that the status code is 200 ,If the user Hits the API [Config] |  | /auth/v1/app-config | bearer token | [5 empty] | Pass |  | Karthikeyan k | 21/02/2024
EMC_02 |  |  | API | Config | Verify that the user modified time , If the user Hits the API[Config] |  | /auth/v1/app-config | bearer token | [5 empty] | Pass |  | Karthikeyan k | 21/02/2024
EMC_03 |  |  | API | Config | Verify that the user App version name , If the user Hits the API[Config] |  | /auth/v1/app-config | bearer token | [5 empty] | Pass |  | Karthikeyan k | 21/02/2024
EMC_04 |  |  | API | Config | Verify that the target ,If the user hits the API [Config] |  | /auth/v1/app-config | bearer token | [5 empty] | Pass |  | Karthikeyan k | 21/02/2024
EMC_05 |  |  | API | Config | Verify that the version , If the user hits the API[Config] |  | /auth/v1/app-config | bearer token | [5 empty] | Pass |  | Karthikeyan k | 21/02/2024
EMC_06 |  |  | API | Config | Verify that the description , If the user hits the API[Config] |  | /auth/v1/app-config | bearer token | [5 empty] | Pass |  | Karthikeyan k | 21/02/2024
EMC_07 |  |  | API | Config | Verify that the created at , If the user hits the API[Config] |  | /auth/v1/app-config | bearer token | [5 empty] | Pass |  | Karthikeyan k | 21/02/2024
EMC_08 |  |  | API |  |  |  | /auth/v1/app-config | bearer token
EMC_09 |  |  | API |  |  |  | /auth/v1/app-config | bearer token
EMC_10 |  |  | API

## Child mode
Test Case ID | Priority | Category/ module | Test Type | API Name | Test Objectives | Test procedure | API End Point | Auth | Request Body | Expected Status Code | Expected Response Body | Expected Result | Actual Result | Status | Bug id | Tested By | Tested on
EMC_01 | P0 |  | API | Child mode | Verify that the status code is 200 [Child mode ] | 1. Hit the API | childmode/v1 | Bearer token |  |  | "active": false, "max_speed": 18, "is_new": false |  |  | Pass |  | Karthikeyan k | 2024-05-02
| P1 |  | API | Child mode | Verify that the active state of child mode | 1. Hit the API | childmode/v1 | Bearer token |  |  | "active": false, "max_speed": 18, "is_new": false |  |  | Pass |  | Karthikeyan k | 2024-05-02
| P1 |  | API | Child mode | Verify that the max speed of child mode settings | 1. Hit the API | childmode/v1 | Bearer token |  |  | "active": false, "max_speed": 18, "is_new": false |  |  | Pass |  | Karthikeyan k | 2024-05-02
| P0 |  | API | Child mode | Verify that the user as new or existing user | 1. Hit the API | childmode/v1 | Bearer token |  |  | "active": false, "max_speed": 18, "is_new": false |  |  | Pass |  | Karthikeyan k | 2024-05-02
| P1 |  | API | Child mode | Verify that the status code 200 after a successful OTP validation | 1. Hit the API | childmode/v1 | Inheritance from parent | [5 empty] | Pass |  | Karthikeyan k | 2024-05-02
| P1 |  | API | Child mode | Verify that the response as null after a successful OTP validation | 1. Hit the API | childmode/v1 | Inheritance from parent | [5 empty] | Pass |  | Karthikeyan k | 2024-05-02
| P0 |  | API | Child mode | Verify that the status code is 400 , If the API get errors | 1. Hit the API | childmode/v2 | Inheritance from parent | [5 empty] | Pass |  | Karthikeyan k | 22/02/2024
| P1 |  | API | Child mode | Verify that the message "Empty result" ,If the API get errors | 1. Hit the API | childmode/v3 | Inheritance from parent | [5 empty] | Pass |  | Karthikeyan k | 22/02/2024
| P0 |  | API | Child mode | Verify that the status code is 401 , If the user selects NO Auth as token | 1. Hit the API | childmode/v3 | No Auth | [5 empty] | Pass |  | Karthikeyan k | 22/02/2024
| P0 |  | API | Child mode | Verify that the message "Invalid token" ,If the API gets errors | 1. Hit the API | childmode/v4 | No Auth | [5 empty] | Pass |  | Karthikeyan k | 22/02/2024
|  |  | API | Child mode | Verify that the message "Expired token " ,If API token get expire | 1. Hit the API | childmode/v1 | Inheritance from parent | [5 empty] | Pass |  | Karthikeyan k | 22/02/2024
|  |  | API | Child mode
|  |  | API | Child mode
|  |  | API | Child mode
|  |  | API | Child mode
|  |  | API | Child mode
|  |  | API | Child mode
|  |  | API | Child mode
|  |  | API | Child mode
|  |  | API | Child mode
|  |  | API | Child mode
|  |  | API | Child mode

## Notifications
Test Case ID | Priority | Category/ module | Test Type | API Name | Test Objectives | Test procedure | API End Point | Auth | Request Body | Expected Status Code | Expected Response Body | Expected Result | Actual Result | Status | Bug id | Tested By | Tested on
EM_01 | P0 |  | API | Notification | Verify that status code is 200 , if user selectr the bearer tocken and hit the Noftication API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  | API should be functionally working with correct status code and respose body |  | Pass |  | Karthikeyan k | 20/02/2024
| P0 |  | API | Notification | Verify that the status code is 401 , If user select the No auth and hit the API | 1. Hit the API | /notification/v1/ | bearer token |  | 401 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P2 |  | API | Notification | Verify that the status message is invalid token , if API failed | 1. Hit the API | /notification/v1/ | bearer token |  | 401 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the date of the notification, if user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 401 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify the id of the notification ,if user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the category of the notification , if user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the title of the notification ,if user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the body of the notification, if the user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the created date notification ,if the user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the seen status of the notification , if user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the category as engineering mode , if user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the title as engineering mode[Lab mode], if the user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | verify that the body as engineering mode activate message[Lab mode activated ] ,If user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the seen status of the engineering mode [Lab mode] ,If user hits the API. | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the title as engineering mode[Urban mode], if the user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | verify that the body as engineering mode activate message[ urban mode activated ] ,If user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify the seen status of the engineering mode [ urban mode] ,If the user hits the API. | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the title as engineering mode[Fitness mode], if the user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | verify that the body as engineering mode activate message[ Fitness mode activated ] ,If user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify the seen status of the engineering mode [ Fitness mode] ,If the user hits the API. | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the title as engineering mode[Eco mode], if the user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | verify that the body as engineering mode activate message[ Eco mode activated ] ,If user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify the seen status of the engineering mode [ Eco mode] ,If the user hits the API. | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the title as child mode ,If the user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the body as child mode[Your child mode is activated] ,If the user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the seen status of the child mode , If user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the body as child mode[Your child mode is de-activated] ,If the user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
| P1 |  | API | Notification | Verify that the seen status of the child mode , If user hits the API | 1. Hit the API | /notification/v1/ | bearer token |  | 200 |  |  |  | Pass |  | Karthikeyan k | 20/02/2024
|  |  | API | [12 empty] | Karthikeyan k
|  |  | API | [12 empty] | Karthikeyan k
|  |  | API | [12 empty] | Karthikeyan k
|  |  | API | [12 empty] | Karthikeyan k
Karthikeyan k

## Engineering modes
Test Case ID | Priority | Category/ module | Test Type | API Name | Test Objectives | Test procedure | API End Point | Auth | Request Body | Expected Status Code | Expected Response Body | Expected Result | Actual Result | Status | Bug id | Tested By | Tested on
EME_01 | P0 | Engineering mode | API | Enginerring modes | Verify that the status code is 200 , If the user hits the API[Engineering mode] | Hits the API | {{domain}}/engmode/v1 | Bearer Token | VIn:E1ABCD | 200 |  | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 22/02/2024
EME_02 | P1 | Engineering mode | API | Enginerring modes | Verify that the staus code is 400 , If the API Fails | Hits the API | {{domain}}/engmode/v2 | Bearer Token | VIn:E1ABCD | 400 |  | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 22/02/2024
EME_03 | P1 | Engineering mode | API | Enginerring modes | Verify that the mode of the user , If user hits the API[Engineering modes] | Hits the API | {{domain}}/engmode/v3 | Bearer Token | VIn:E1ABCD | 200 |  | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 22/02/2024
EME_04 | P1 | Engineering mode | API | Enginerring modes | Verify that the lab setting data , If the user Hits the API[Engineering modes] | Hits the API | {{domain}}/engmode/v4 | Bearer Token | VIn:E1ABCD | 200 |  | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 22/02/2024
EME_05 | P1 | Engineering mode | API | Enginerring modes | Verify that the lab setting A value , If the user hits the API[Engineering modes] | Hits the API | {{domain}}/engmode/v5 | Bearer Token | VIn:E1ABCD | 200 |  | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 22/02/2024
EME_06 | P1 | Engineering mode | API | Enginerring modes | Verify that the lab setting B value , If the user hits the API[Engineering modes] | Hits the API | {{domain}}/engmode/v1 | Bearer Token | VIn:E1ABCD | 200 |  | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 22/02/2024
EME_07 | P1 | Engineering mode | API | Enginerring modes | Verify that the lab setting C value , If the user hits the API[Engineering modes] | Hits the API | {{domain}}/engmode/v1 | Bearer Token | VIn:E1ABCD | 200 |  | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 22/02/2024
EME_08 | P1 | Engineering mode | API | Enginerring modes | Verify that the lab setting D value , If the user hits the API[Engineering modes] | Hits the API | {{domain}}/engmode/v1 | Bearer Token | VIn:E1ABCD | 200 |  | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 22/02/20204
EME_09 | P1 |  | API | Enginerring modes | Verify that the lab setting E value , If the user hits the API[Engineering modes] | Hits the API | {{domain}}/engmode/v1 | Bearer Token | VIn:E1ABCD | 200 |  | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 22/02/2024
EME_10 | P1 | Engineering mode | API | Enginerring modes | Verify that the throttle cut-off status ,If the user hits the API[Engineering modes] | Hits the API | {{domain}}/engmode/v2 | Bearer Token | VIn:E1ABCD | 200 |  | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 22/02/2024
EME_11 | P1 | Engineering mode | API | Enginerring modes | Verify that the motor -resistance , If the user hits the API[Engineering modes] | Hits the API | {{domain}}/engmode/v3 | Bearer Token | VIn:E1ABCD | 200 |  | API should be functionally working with correct status code and respose body | Status Code:200 Response Body: | Pass |  | Karthikeyan k | 22/02/2024

## Community
Test Case ID | Priority | Category/ module | Test Type | API Name | Test Objectives | Test procedure | API End Point | Auth | Request Body | Expected Status Code | Expected Response Body | Expected Result | Actual Result | Status | Bug id | Tested By | Tested on
|  | Community | API | Community Get event details | Verify that the response status code is 200, if the user hits the community (get event community) |  | /community/v1/events/20d0ea4b-5b88-45f3-966a-65c94b2051a3 | [6 empty] | Pass
|  | Community | API | Community Get event details | Verify that the event id , if the user hits the community get | [8 empty] | Pass
|  | Community | API | Community Get event details | Verify that the event title , if the user hits the community get | [8 empty] | Pass
|  | Community | API | Community Get event details | Verify that the thumbnail image present ,if user hits the community get | [8 empty] | Pass
|  | Community | API | Community Get event details | Verify that the start at (Location) ,if the user hits the community get | [8 empty] | Pass
|  | Community | API | Community Get event details | Verify that the end at (Location) ,If the user hits the community get | [8 empty] | Pass
|  | Community | API | Community Get event details | Verify that the area ,If the user hits the community get | [8 empty] | Pass
|  | Community | API | Community Get event details | Verify that the latitude ,If the user hits the community get
|  | Community | API | Community Get event details | Verify that the longitude ,If the user hits the community get
|  | Community | API | Community Get event details | Verify that the rules , If the user hits the community get
|  | Community | API | Community Get event details | Verify that the eligibility ,If the user hits the community get
|  | Community | API | Community Get event details | Verify that the goodies ,If the user hits the community get
|  | Community | API | Community Get event details | Verify that the questions ,If the user hits the community get
|  | Community | API | Community Get event details | Verify that the leaderboard ,If the user hits the community get
|  | Community | API | Community Get event details | Verify that the participants ,If the user hits the community get
|  | Community | API | Community Get event details | Verify that the Status ,If the user hits the community get