## December 2023
Date | Name | Task | POD-Project Name | Story/Bug ID/Task/Sub Task | Story/Bug/Task Summary | Count (TC Design/ Execution) | Severity/Priority | Bug Verification Status
2023-12-11 | Karthikeyan Kumar | Demo/Grooming | Emotorad | How E-bike will operating and how to pair e-bike with app
2023-12-11 | Karthikeyan Kumar | Introduction call | Emotorad | NA
2023-12-11 | Karthikeyan Kumar | Documentation | Emotorad | NA
2023-12-12 | Karthikeyan Kumar | Exploratory Testing | Emotorad | Pair the app with E-bike
2023-12-12 | Karthikeyan Kumar | TC Design | Emotorad | Creating the modules list |  | 25 | Highest
2023-12-12 | Karthikeyan Kumar | TC Design | Emotorad | Writing test cases for On -boarding and profile creation PRD
2023-12-12 | Karthikeyan Kumar | Demo/Grooming | Emotorad | Testing the E-bike and rideout for 5 minutes , covering the bluetooth senarioes (on &off) while ride the E-bike
2023-12-12 | Karthikeyan Kumar | Adhoc Task | Emotorad | Give Kt session about Jira and Jira filter .
2023-12-13 | Karthikeyan Kumar | TC Design | Emotorad | Writing test cases for On -boarding and profile creation PRD |  | 35 | Highest
2023-12-13 | Karthikeyan Kumar | Team call | Emotorad | Project kick off call
2023-12-13 | Karthikeyan Kumar | TC Execution | Emotorad | Desining Test cases on on-boarding and profile creation PRD |  | 5
2023-12-13 | Karthikeyan Kumar | Team call | Emotorad | Amigo Alpha -phase Feeback (Pune & Bangalore)
2023-12-14 | Karthikeyan Kumar | TC Design | Emotorad | Designing Test cases on Home page PRD |  | 40 | Highest
2023-12-14 | Karthikeyan Kumar | Bug Reported | Emotorad | Reviewing the Amigo Alpha Phase -1 (Customer Clinic Report) and reporting issues .
2023-12-14 | Karthikeyan Kumar | Team call | Emotorad | Kt session 1
2023-12-14 | Karthikeyan Kumar | Adhoc Task | Emotorad | Adhoc testing testing done on home page
2023-12-15 | Karthikeyan Kumar | TC Design | Emotorad | Test case design on Onboard & home page |  | 56 | Highest
2023-12-15 | Karthikeyan Kumar | Bug Reported | Emotorad | Reviewing the Amigo Alpha Phase -1 (Customer Clinic Report) and reporting issues .
2023-12-15 | Karthikeyan Kumar | Demo/Grooming | Emotorad | Kt session on connectivity & ride details features
2023-12-15 | Karthikeyan Kumar | QA Estimation | Emotorad | Reviewing PRD and Plan test estimation
2023-12-15 | Karthikeyan Kumar | Bug Verification | Emotorad | Discussing the existing issues .
2023-12-18 | Karthikeyan Kumar | Bug Verification | Emotorad | Discussing the existing issues .
2023-12-18 | Karthikeyan Kumar | Bug Verification | Emotorad | Structuring all the existing bugs and creating labels & assigning them to the developers.
2023-12-18 | Karthikeyan Kumar | Demo/Grooming | Emotorad | Kt session cloud (Back end testing )
2023-12-18 | Karthikeyan Kumar | TC Design | Emotorad | Desigining test cases on PRD's |  | 45
2023-12-18 | Karthikeyan Kumar | Report Preperation | Emotorad | DSR Report preparation
2023-12-18 | Karthikeyan Kumar | Bug Reported | Emotorad | Reporting Bugs
2023-12-18 | Karthikeyan Kumar | Team call | Emotorad | EMotorad team call
2023-12-18 | Karthikeyan Kumar | KT Videos | Emotorad | Kt session on manual testing
2023-12-18 | Karthikeyan Kumar | Bug Verification | Emotorad | bug verification done on existing jira's
2023-12-19 | Karthikeyan Kumar | TC Design | Emotorad | Designing Test cases on Home page PRD |  | 45
2023-12-19 | Karthikeyan Kumar | Bug Reported | Emotorad | Exploring the application with two new Apk's
2023-12-19 | Karthikeyan Kumar | Bug Verification | Emotorad | Bug verification done on existing jira's
2023-12-19 | Karthikeyan Kumar | KT Videos | Emotorad | Kt session on Designing testing documnets and test cases.
2023-12-20 | Karthikeyan Kumar | Bug Reported | Emotorad | Bug Reported on verifying fix issues on latest Apk |  | 2
2023-12-20 | Karthikeyan Kumar | TC Design | Emotorad | Designing test cases on Connectivity |  | 45
2023-12-20 | Karthikeyan Kumar | KT Videos | Emotorad | Kt session on API testing
2023-12-20 | Karthikeyan Kumar | Adhoc Task | Emotorad | Working on New APK (sanity testing done on Map features)
2023-12-21 | Karthikeyan Kumar | TC Design | Emotorad | Designing test cases on Connectivity |  | 45
2023-12-21 | Karthikeyan Kumar | Exploratory Testing | Emotorad | New APK shared to check on features Bike colour And Bike VIN
2023-12-21 | Karthikeyan Kumar | Bug Reported | Emotorad | Exploring the application and Reporting bug's |  | 3 | Highest
2023-12-21 | Karthikeyan Kumar | Team call | Emotorad | Emotorad ¦ Qualitrix QA Governance Call
2023-12-21 | Karthikeyan Kumar | Team call | Qualitrix | Corporate Mediclaim Policy Renewal - Dec 21, 2023
2023-12-21 | Karthikeyan Kumar | KT Videos | Qualitrix | Kt session on API testing
2023-12-21 | Karthikeyan Kumar | Bug Reported | Emotorad | Validation on latest APK -21st december
2023-12-22 | Karthikeyan Kumar | Bug Verification | Emotorad | 7 Bug verifications assigned to my name , Need to check and update within today |  | 7 | Highest | Closed
2023-12-22 | Karthikeyan Kumar | TC Design | Emotorad | Designing test cases on Connectivity & Maps |  | 45
2023-12-22 | Karthikeyan Kumar | TC Update | Emotorad | TC update
2023-12-22 | Karthikeyan Kumar | KT Videos | Emotorad | API Kt session .
2023-12-22 | Karthikeyan Kumar | Exploratory Testing | Emotorad | Exploring the new features on New APK(Dark mode & Ride Dashboard)
26-12-2023 | Karthikeyan Kumar | TC Design | Emotorad | Designing test cases on Maps |  | 45
26-12-2023 | Karthikeyan Kumar | Bug Reported | Emotorad | Exploring the application and Reporting bug's |  | 2
26-12-2023 | Karthikeyan Kumar | TC Update | Emotorad | TC updated on connectivity PRD
26-12-2023 | Karthikeyan Kumar | KT Videos | Emotorad | Kt session on API testing
26-12-2023 | Karthikeyan Kumar | Team call | Emotorad | Fun Activities |  | 1
26-12-2023 | Karthikeyan Kumar | Bug Verification | Emotorad | Bug verification done on existing creating bug's
27-12-2023 | Karthikeyan Kumar | Team call | Emotorad | Team call
27-12-2023 | Karthikeyan Kumar | TC Design | Emotorad | Designing test cases on Maps |  | 45
27-12-2023 | Karthikeyan Kumar | KT Videos | Emotorad | KT session on Backend testing.
27-12-2023 | Karthikeyan Kumar | Bug Reported | Emotorad | Exploring the application and Reporting bug's |  | 2
28-12-2023 | Karthikeyan Kumar | TC Design | Emotorad | Designing test cases on Engineering modes |  | 45
28-12-2023 | Karthikeyan Kumar | KT Videos | Emotorad | KT Session on jira and zephyr scale.
28-12-2023 | Karthikeyan Kumar | KT Videos | Emotorad | KT Session Assement
28-12-2023 | Karthikeyan Kumar | Bug Reported | Emotorad | Exploring the application and Reporting bug's
28-12--2023 | Karthikeyan Kumar | KT Videos | Emotorad | KT session about cloud .
28-12-2023 | Karthikeyan Kumar | TC Update | Emotorad | Tc update.
28-12-2023 | Karthikeyan Kumar | Demo/Grooming | Emotorad | EM-bike Demo
29-12-2023 | Karthikeyan Kumar | Bug Reported | Emotorad | Exploring the application and Reporting bug's on latest APK 28th Dec |  | 2
29-12-2023 | Karthikeyan Kumar | TC Design | Emotorad | Designing test cases on Engineering modes and ride details.
29-12-2023 | Karthikeyan Kumar | Team call | Emotorad | Discussion about Existing jira's
29-12-2023 | Karthikeyan Kumar | Demo/Grooming | Emotorad
29-12-2023 | Karthikeyan Kumar | Exploratory Testing | Emotorad
2024-02-01 | Karthikeyan Kumar | Team call | Emotorad | Discussion with Jagrit about test case validation.
2024-02-01 | Karthikeyan Kumar | TC Update | Emotorad | Update Test case |  | 40
2024-02-01 | Karthikeyan Kumar | TC Execution | Emotorad | Execution Test cases on -boarding and profile creation PRD
2024-02-01 | Karthikeyan Kumar | KT Videos | Emotorad | Kt session for API and Postman tool
2024-02-01 | Karthikeyan Kumar | Bug Reported | Emotorad | Exploring the application and Reporting bug's |  | 7
2024-03-01 | Karthikeyan Kumar | TC Execution | Emotorad | Execution Test cases on -boarding and profile creation PRD |  | 44
2024-03-01 | Karthikeyan Kumar | Bug Reported | Emotorad | Exploring the application and Reporting bug's of using Alpha APK Build . |  | 3
2024-03-01 | Karthikeyan Kumar | TC Update | Emotorad | Test case update on existing PRD
2024-04-01 | Karthikeyan Kumar | TC Execution | Emotorad | Execution Test cases on -boarding and profile creation PRD
2024-04-01 | Karthikeyan Kumar | Team call | Emotorad | Stand up call with team
2024-04-01 | Karthikeyan Kumar | Adhoc Task | Emotorad | Verify Live data was stored aligned correctly .
2024-04-01 | Karthikeyan Kumar | Adhoc Task | Emotorad | Tested Compass mode and connectivity
2024-04-01 | Karthikeyan Kumar | Team call | Emotorad | QA governance call
2024-04-01 | Karthikeyan Kumar | Team call | Emotorad | Backend testing estimation plan call
2024-04-01 | Karthikeyan Kumar | KT Videos | Emotorad | Getting knowledge about backend testing from manoj
2024-04-01 | Karthikeyan Kumar | Bug Reported | Emotorad | Exploring the application and Reporting bug's
2024-04-01 | Karthikeyan Kumar | Team call | Emotorad | App Review Meeting
2024-04-01 | Karthikeyan Kumar | Exploratory Testing | Emotorad | Check the functionality on New Alpha Apk Build .
2024-05-01 | Karthikeyan Kumar | Team call | Emotorad | Stand up call with team
2024-05-01 | Karthikeyan Kumar | Team call | Emotorad | App Review Meeting
2024-05-01 | Karthikeyan Kumar | TC Design | Emotorad | Designing test cases on Hardware and Backend.
2024-05-01 | Karthikeyan Kumar | TC Update | Emotorad | Update Test case on existing PRD
2024-05-01 | Karthikeyan Kumar | KT Videos | Emotorad | Final Assessment
2024-05-01 | Karthikeyan Kumar | Exploratory Testing | Emotorad | Check the functionality on New Alpha Apk Build .
2024-08-01 | Karthikeyan Kumar | TC Design | Emotorad | Designing Testcases on Hardware and backend
2024-08-01 | Karthikeyan Kumar | TC Execution | Emotorad | Executing testcases on Home page
2024-08-01 | Karthikeyan Kumar | Team call | Emotorad | Stand up call with team
2024-08-01 | Karthikeyan Kumar | Bug Reported | Emotorad | Reporting bugs .
2024-08-01 | Karthikeyan Kumar | KT Videos | Emotorad | KT session Given for Anurag
2024-08-01 | Karthikeyan Kumar | Team call | Emotorad | Team call
2024-08-01 | Karthikeyan Kumar | Adhoc Task | Emotorad | Setup the cloud softwares
2024-09-01 | Karthikeyan Kumar | Team call | Emotorad | Team call about discussing the existing issues on Alpha Release
2024-09-01 | Karthikeyan Kumar | Adhoc Task | Emotorad | Update the Jira labels in all Existing jiras
2024-09-01 | Karthikeyan Kumar | TC Execution | Emotorad | Testcase execution on Alpha Release.
2024-09-01 | Karthikeyan Kumar | Team call | Emotorad | Daily Stand up call
2024-09-01 | Karthikeyan Kumar | TC Design | Emotorad | Testcase Designing on backend and Hardwarev
2024-10-01 | Karthikeyan Kumar | Team call | Emotorad | Team meeting about existing issues -35 Minutes
2024-10-01 | Karthikeyan Kumar | Demo/Grooming | Emotorad | Checking the connectivity issues on EM-bike -20 mins
2024-10-01 | Karthikeyan Kumar | Bug Reported | Emotorad | Need tor raise bug on connectivity
2024-10-01 | Karthikeyan Kumar | TC Execution | Emotorad | Testcase execution on connectivity and navigation
2024-10-01 | Karthikeyan Kumar | TC Design | Emotorad | Tesatcase designing on Hardware
2024-10-01 | Karthikeyan Kumar | Team call | Emotorad | Standup call - 45 Minutes
2024-10-01 | Karthikeyan Kumar | KT Videos | Emotorad | Hardware Kt session -20 Minutes
2024-10-01 | Karthikeyan Kumar | Adhoc Task | Emotorad | Testing smart lock features
2024-11-01 | Karthikeyan Kumar | Team call | Emotorad | Stand up call
2024-11-01 | Karthikeyan Kumar | Team call | Emotorad | Qualirix QA goverance call
2024-11-01 | Karthikeyan Kumar | TC Execution | Emotorad | Testcase execution on navigation
2024-11-01 | Karthikeyan Kumar | TC Design | Emotorad | Testcase design on Backend and database
2024-11-01 | Karthikeyan Kumar | Adhoc Task | Emotorad | JIra updation
2024-11-01 | Karthikeyan Kumar | Adhoc Task | Emotorad | Call with Jyesh
2024-11-01 | Karthikeyan Kumar | Adhoc Task | Emotorad | Updated the JIra
2024-11-01 | Karthikeyan Kumar | Adhoc Task | Emotorad | App Review Meeting - one hour
2024-12-01 | Karthikeyan Kumar | Exploratory Testing | Emotorad | EM-Bike Testing on Latest APK build
2024-12-01 | Karthikeyan Kumar | Bug Reported | Emotorad | Reporting bugs on Alpha
2024-12-01 | Karthikeyan Kumar | TC Execution | Emotorad | Test case execution on Maps
2024-12-01 | Karthikeyan Kumar | Team call | Emotorad | Team Standup call
2024-12-01 | Karthikeyan Kumar | Team call | Emotorad | Daily standup call
17-01-2024 | Karthikeyan Kumar | Adhoc Task | Emotorad | Verifying the Beta issues
17-01-2024 | Karthikeyan Kumar | Bug Reported | Emotorad | Reporting bugs on latest Beta Apk Build.
17-01-2024 | Karthikeyan Kumar | Exploratory Testing | Emotorad | Explore the application on latest beta build
17-01-2024 | Karthikeyan Kumar | Team call | Emotorad | Call with jayanth
17-01-2024 | Karthikeyan Kumar | TC Execution | Emotorad | Testcase execution on backend Testing
17-01-2024 | Karthikeyan Kumar | TC Update | Emotorad | Updating testcase.
18-01-2024 | Karthikeyan Kumar | Exploratory Testing | Emotorad | Expore the application on New build .
18-01-2024 | Karthikeyan Kumar | Bug Reported | Emotorad | Bug reported on new beta3 build
18-01-2024 | Karthikeyan Kumar | Team call | Emotorad | Daily stand up call.
18-01-2024 | Karthikeyan Kumar | TC Design | Emotorad | Designing testcases on Child mode
18-01-2024 | Karthikeyan Kumar | TC Execution | Emotorad | Executing testcases on backend.
18-01-2024 | Karthikeyan Kumar | TC Update | Emotorad | Updating the existing testcases.
19-01-2024 | Karthikeyan Kumar | TC Design | Emotorad | Designing testcase on Child mode PRD
19-01-2024 | Karthikeyan Kumar | Team call | Emotorad | Daily standup call.
19-01-2024 | Karthikeyan Kumar | TC Execution | Emotorad | Execution test cases on Engineering mode
19-01-2024 | Karthikeyan Kumar | TC Update | Emotorad | Updating the existing test cases.
22-01-2024 | Karthikeyan Kumar | Adhoc Task | Emotorad | Sanity testing on Beta 3 Build.
22-01-2024 | Karthikeyan Kumar | Bug Reported | Emotorad | Bug reported on new beta3 build
22-01-2024 | Karthikeyan Kumar | Team call | Emotorad | Daily stand up call
22-01-2024 | Karthikeyan Kumar | TC Design | Emotorad | Testcase Execution on child mode.
22-01-2024 | Karthikeyan Kumar | TC Execution | Emotorad | Testcase design on smart lockers and smart speakers .
22-01-2024 | Karthikeyan Kumar | Team call | Emotorad | Team meeting
23-01-2024 | Karthikeyan Kumar | TC Design | Emotorad | Testcase design on smart lockers and smart speakers .
23-01-2024 | Karthikeyan Kumar | Team call | Emotorad | Daily standup call
23-01-2024 | Karthikeyan Kumar | Bug Reported | Emotorad | Bug reported on Smart lock accessories
23-01-2024 | Karthikeyan Kumar | TC Execution | Emotorad | Testcase execution on smart lock accessories.
24-01-2024 | Karthikeyan Kumar | TC Execution | Emotorad | Test case execution on smart lock .
24-01-2024 | Karthikeyan Kumar | Demo/Grooming | Emotorad | EM-Bike testing on beta 3 build
24-01-2024 | Karthikeyan Kumar | Team call | Emotorad | Daily standup call
24-01-2024 | Karthikeyan Kumar | TC Design | Emotorad | Designing test cases on smart speakers .
24-01-2024 | Karthikeyan Kumar | Bug Reported | Emotorad | Reported bugs on Smart Lock and engineering modes
24-01-2024 | Karthikeyan Kumar | Exploratory Testing | Emotorad | Validating new smart locks
25-01-2024 | Karthikeyan Kumar | Team call | Emotorad | Daily standup call
25-01-2024 | Karthikeyan Kumar | Exploratory Testing | Emotorad | Sanity testing on new beta 3 build.
25-01-2024 | Karthikeyan Kumar | TC Design | Emotorad | Testcase design on speakers
29-01-2024 | Karthikeyan Kumar | TC Design | Emotorad | Testcase design on speakers
29-01-2024 | Karthikeyan Kumar | Team call | Emotorad | Daily stand call
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad
| Karthikeyan Kumar |  | Emotorad